## Meetings
Scrum tri-weekly meetings | Member |  |  | Member |  |  | Member |  |  | Member
Scrum Master: Joshua Wallace
Start Date | Joshua Wallace |  |  | Meli Jimenez |  |  | Damon Chadic |  |  | Julio Franco
Monday, April 11 | What did you do before last scrum meeting? | What do you plan to do from today through before the next scrum meeting? | Are there any roadblocks? | What did you do before last scrum meeting? | What do you plan to do from today through before the next scrum meeting? | Are there any roadblocks? | What did you do before last scrum meeting? | What do you plan to do from today through before the next scrum meeting? | Are there any roadblocks? | What did you do before last scrum meeting? | What do you plan to do from today through before the next scrum meeting? | Are there any roadblocks?
End Date
Friday, April29
Monday, April 11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Wednesday, April 13 | I put the stories into the SCRUM board and assigned them to team members. I also assigned tasks with due dates for team members including one for Meli to contact the film department to get us videos. | Plan to get Ruby on Rails set up and put skeleton of app onto Github | No | Contacted the film department. Made list of faculty members and film makers on campus. | Working on the logo. Maybe just draft the front end. How it is going to look. What it will look like. | If they don't answer their emails we wont' have any movies. Will need to put placeholders. | Working on getting familiar with Ruby on Rails. Tutorials. Figuring out how you can get the product to look how he wants. | More of the same. Till he can get familiar with it. | No. Waiting for Joshua to put the Ruby stuff on Github. | Set up the SCRUM board/planning/meeting sheets. | Start on sketches for the design for the mobile app. | No
Friday, April 15 | I researched Ruby/Rails versions and found IDE. Uploaded template to git. | Set up the site on AWS. Get movies from Tommy. | Not at the moment. | Got the film department support. They are emailng all the film studetns on campus and directors. We are getting the rights. | Make a flier and finish the logo. | Not yet. | Nothing specific, just more learning with Ruby on Rails. | Install RubyMine, update Git, update the main view in the project. | Roadblocks: checking Slack. | Worked on desigingn the UI for both iPhone and iPad. | More of the same. | None at the moment.
Monday, April 18 | Created email addresss info@whatthefilm.co | Still need to get the site bones put up on AWS. Will need to make an EC-2 Instance that works with Rails. Will point the domain to our EC-2. | Learning how Ruby server code works. | Designed a flier. Finished the logo. Sent flier to film department and asked them to send it to students and faculty. Also cotacted Porter college. Brainstorming for the front end. | Plans on working on the front end now. Design. | Good for now. | Installed RubyMine. Group Evaluation. | Working on the front end. Meeting up with Meli to work on it together. Brainstorm what you want it to look like. | None for now. | Came to conclusion that its better to use a generic design and then change it to match the web design later. Environment setup complete. Decided Inital UI. | Coding simple design. | Homework from other classes.
Wednesday, April 20 | Researched using EC2 with Ruby on Rails | Putting the site onto EC2 | None. | Browsed around and pencil drafted some layouts that we can use. Played around with Photoshop a little bit. Talked about needing films in her film class. | Drafting more stuff and sending it to Damon. | Going to LA this weekend. | Studied Ruby. Coming up with design on front end. | Planning on meeting with Meli and working on a first draft of web design. | Mom is coming to town this weekend. | Started implementing simple navigation for the the movie list design. Tested coding the media player so that it can stream a file. | More of the same. Adding more funcationality | No
Friday, April 22 | Got our EC2 Instance running on AWS. | Connect domain with AWS and Get sample view working on EC2. | None. | Worked on the front end design and layout | Finish the front end home page layout and send to Damon | Going to LA this weekend. | Studied Ruby. Made plans with Meli to meet on Sunday. | Meeting with Meli on Sunday RE design. | Mom is coming to town this weekend. | Worked on updating movie details screen. | Continue working on main screen and movie detail screen. | Studying for midterm next week.
Monday, April 25 | Spent a lot of time trying to get Ruby on Rails to run on AWS. Then tried doing Heroku. | Need to decide on AWS or Heroku. Need to spend a lot of time figuring out how the database connects to the application. | Not familiar with Ruby or Postgres. | Worked on the front end design and layout. Contacted filmmakers | Finish the front page | None | Ruby practice. Didn't meet with Melly | plan meeting time with Melly | laptop charger lost | Unable to make progress, preparing for cs102 midterm and internship interview | Will put in around 20+ hours of work this weekend | Yes, cs102 midterm and interview.
Wednesday, April 27 | Continued to try to get Ruby on AWS. Failed. | Will make landing page for our site for people interested in giving us their films. Will work on Node onto AWS. Will download the Public Domain movies. | My AWS account got hacked into and I received $38,000 in charges. I had to deal with canceling my credit card and fixing my account. Also Ruby is not as easy as I thought. | Finished the front end design Contacted filmmakers | Design and code the HTML5 player Meet with Damon | Find the time | Ruby work, preparing for midter | Meeting with Meli on Thursday @ 12:10 | laptop charger lost | Unable to make progress, preparing for cs102 midterm and internship interview | Will put in around 20+ hours of work this weekend | Yes, cs102 midterm and interview.
Friday, April 29 | Made landing page and spent more time with AWS getting Node/Koa app running. | Will try to get Node up. | I have to go to OC this weekend. | Contacted more filmmakers | Met with Damon | Running against time | Worked on some potential code for UI | Meeting with Meli, install bootstrap, work on UI | Laptop charger lost, going to Berkely this weekend. | simple screen with a tableview and movie details screen with placeholders completed, able to stream and test file. | will wrap up the initial 2 views, movie grid and movie details screen | Not anymore

## Board
User Story | To-do | In Progress | Done
As a user, I want to be able to click on a movie cover so that I can watch a film |  |  | Set Up Node/Webstorm (JW)
Set Up AWS (JW)
Design Simple iOS (JF)
Design Simple Web (MJ & DC)
Design Logo (MJ)
Video Serving API (JW)
Implement iOS UI (JF)
Implement Web UI (MJ & DC)
Hook Up iOS with Server
Hook Up Web with Server
Set Up Xcode (JF)
Get rights to movies (MJ)
As a user, I want to be able to use a grid of movie covers so that I can find the film I want. | Design grid iOS UI
Design grid web UI
Implement grid iOS UI
Implement grid web UI

## Burnup Chart
Task | Time (estimated) | Time (spent) | Time (left) | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Set Up Ruby | 4 | 4 | 0.5 | 14: 2; 17: 1; 19: 0.5
Set Up AWS | 6 | 11.5 | 0 | 19: 0.5; 21: 1; 23: 3; 26: 3; 28: 4
Design Simple iOS UI | 5 | 5 | 4.5 | 14: 0.5
Design Simple Web UI | 6 | 8 | 0 | 19: 1; 23: 3; 24: 2; 25: 2
Design Logo | 2 | 2 | 0.83334 | 14: 1; 16: 0.16666
Implement iOS UI | 20 | 20 | 17 | 20: 1.5; 21: 1; 27: 0.5
Implement Web UI | 15 | 15 | 15
Video Serving API | 20 | 0 | 20
Hook Up iOS with Server | 8 | 8 | 8
Hook Up Web with Server | 10 | 10 | 10
Get rights to movies | 3 | 6.5 | 0 | 13: 0.5; 14: 0.5; 16: 0.5; 17: 2; 21: 0.5; 24: 0.5; 28: 2
Design grid iOS UI | 4 | 4 | 3 | bar: 28
Design grid web UI | 4 | 4 | 4
Implement grid iOS UI | 6 | 6 | 5 | bar: 28
Implement grid web UI | 6 | 6 | 6
0
0
Task 17 |  |  | 0
Task 18 |  |  | 0
Task 19 |  |  | 0
Task 20 |  |  | 0
Task 21 |  |  | 0
Task 22 |  |  | 0
Task 23 |  |  | 0
Task 24 |  |  | 0
Task 25 |  |  | 0
Task 26 |  |  | 0
Task 27 |  |  | 0
Task 28 |  |  | 0
Task 29 |  |  | 0
Task 30 |  |  | 0
Task 31 |  |  | 0
Task 32 |  |  | 0
TOTAL | 119 | 110 | 93.83334 | 0.5 | 4 | 0 | 0.66666 | 3 | 0 | 2 | 1.5 | 2.5 | 0 | 6 | 2.5 | 2 | 3 | 0.5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Daily burnout | 0 |  |  | 13: 7; 14: 7; 15: 7; 16: 7; 17: 7; 18: 7; 19: 7; 20: 7; 21: 7; 22: 7; 23: 7; 24: 7; 25: 7; 26: 7; 27: 7; 28: 7; 29: 7
Total time left (from estimate) |  | Estimate | 119 | 112 | 105 | 98 | 91 | 84 | 77 | 70 | 63 | 56 | 49 | 42 | 35 | 28 | 21 | 14 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total time left (from spent) |  | Burnout | 110 | 109.5 | 105.5 | 105.5 | 104.83334 | 101.83334 | 101.83334 | 99.83334 | 98.33334 | 95.83334 | 95.83334 | 89.83334 | 87.33334 | 85.33334 | 82.33334 | 81.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334 | 73.83334

## Retrospective
Retrospective
Start Doing: | We would like to start working on getting the videos to actually stream. We knew this would be the hardest part but it is taking longer than expected.
Stop Doing: | Would like to stop doing design work and get to actual implenetation.
Continue Doing: | We would like to continue looking for more movies to stream. We only have 2 so far and need a lot more if we want to have an actual streaming service.
Stories Completed: | None (Only got 75% of the way on the first user story. We probably should have broken it up into several user stories.)
Stories Not Completed: | 1. As a user, I want to be able to click on a movie cover so that I can watch a film
2. As a user, I want to be able to use a grid of movie covers so that I can find the film I want.